## Local Purchases
Date | Division | Project / Job Code | Project Name | PR Number | Item Description | Requested By | Date Raised | Category | Priority | Estimated Value (BHD) | Current Stage | Assigned Buyer | Supplier Name | PO Number | PO Value (BHD) | Expected Delivery Date | Actual Delivery Date | Days in Current Stage | Remarks / Blockers

## International Purchases
Date | Division | Project / Job Code | Project Name | PR Number | Item Description | Requested By | Date Raised | Category | Priority | Estimated Value (USD) | Current Stage | Assigned Buyer | Supplier Name | Supplier Country | PO Number | PO Value (USD) | Incoterms | Payment Terms | Payment Status | Production Status | Ready Date | Expected Delivery Date | Actual Delivery Date | Days in Current Stage | Remarks / Blockers

## Shipments Tracker
GENERAL |  |  |  | ORDER DETAILS | [5 empty] | ROUTE |  | SHIPPING |  |  | CONTAINER / CARGO |  |  |  |  | DATES |  |  | STATUS | DELAY | REROUTE |  |  | CUSTOMS |  | CLEARING COSTS (BHD) | [8 empty] | TRACKING
Date | Division | Project / Job Code | Project Name | Direction | PO Reference | Supplier / Consignee | Country | Item Description | Incoterms | Origin Port / City | Destination Port / City | Shipment Mode | Carrier / Shipping Line | BL / AWB Number | No. of 20ft Containers | No. of 40ft Containers | No. of 40ft HC Containers | LCL CBM | Total Packages / Pallets | ETD | ETA | Actual Arrival Date | Current Status | Delay Reason | Rerouted (Y/N) | Reroute Reason | Rerouted To (Port/City) | Customs Broker | Customs Status | Cargo Value (BHD) | Customs Duty (BHD) | VAT 10% (BHD) | DO Charges (BHD) | Freight Charges (BHD) | Handling / THC (BHD) | Demurrage / Detention (BHD) | Other Charges (BHD) | Total Clearing Cost (BHD) | Delivered to Warehouse Date | Days Since ETD | Remarks / Delays
0
0
0
0
0

## Escalations & Blockers
Date | Division | Project / Job Code | Project Name | Reference (PR/PO/Shipment) | Type | Description of Issue | Impact Level | Owner / Responsible | Action Required | Target Resolution Date | Status | Resolution Notes

## Delay Reasons Reference
Delay Reason | Category
Port Congestion | Port / Terminal
Vessel Schedule Change | Carrier
Vessel Breakdown / Mechanical Failure | Carrier
Rolled Cargo (Bumped from Vessel) | Carrier
Bad Weather / Rough Seas | Weather
Typhoon / Hurricane / Cyclone | Weather
Customs Documentation Error | Customs
Customs Inspection / Hold | Customs
Missing or Expired Certificates | Documentation
HS Code Misclassification | Customs
Customs Duty Dispute | Customs
Labor Strike / Industrial Action | Labor
Labor / Workforce Shortage | Labor
Container Shortage / Equipment Unavail. | Equipment
Carrier Capacity Constraints | Carrier
Peak Season Congestion | Demand
Geopolitical Conflict / Sanctions | Geopolitical
Canal Restriction (Suez/Panama) | Infrastructure
Piracy / Security Threat | Security
Supplier Production Delay | Supplier
Cargo Damage in Transit | Damage
Incorrect / Incomplete Documentation | Documentation
Booking Cancellation by Carrier | Carrier
Transshipment Delay / Missed Connection | Transit
Inland Transportation Delay | Transport
Port Infrastructure Issue | Infrastructure
Quarantine / Health Inspection | Regulatory
Trade Embargo / Regulatory Change | Regulatory
Force Majeure / Natural Disaster | Force Majeure
Container Detained / Held | Equipment
Payment / LC Issue Blocking Release | Financial
Freight Rate Dispute | Financial
Other (See Remarks) | Other

## Project Codes
Division | Project / Job Code | Project Name | Client / Customer | Status
Delmon Furniture Factory | DFF-2026-001 | Al Fozan Villa | Al Fozan Group | Active
Delmon Furniture Factory | DFF-2026-002 | KFF Showroom Fit-out | KFF | Active
Delmon Furniture Factory | DFF-2026-003 | Hotel Lobby Furniture | Gulf Hotels Group | Active
Delmon Furniture Factory | DFF-MFG-001 | Manufacturing Unit Stock | Internal | Active
AJK Unity | AJK-2026-001 | HVAC Installation - Tower A | ABC Developers | Active
AJK Unity | AJK-2026-002 | Chiller Replacement Project | Ministry of Works | Active
AJK Unity | AJK-2026-003 | MEP Works - Phase 2 | Gulf Construction | Active
Pearl Craft | PC-2026-001 | Royal Palace Interiors | Royal Court | Active
Pearl Craft | PC-2026-002 | Corporate Office Fit-out | NBB Tower | Active
Pearl Craft | PC-2026-003 | Restaurant Interior Design | Hospitality Group | Active
Pearl Craft | PC-MFG-001 | Workshop Stock Production | Internal | Active

## Instructions
AJM Kooheji Group - Supply Chain Daily Input Guide
Overview
This workbook is the single data input source for the Supply Chain Dashboard.
Shipments - Delay Tracking
When a shipment status is set to "Delayed": 1. Select the Delay Reason from the dropdown (33 standardized reasons) 2. See the "Delay Reasons Reference" sheet for the full categorized list 3. Add any additional detail in the Remarks column Delay reason categories include: Port/Terminal, Carrier, Weather, Customs, Documentation, Labor, Equipment, Geopolitical, Infrastructure, Security, Regulatory, Financial, and Force Majeure.
Shipments - Rerouting
When a shipment is rerouted: 1. Set Current Status to "Rerouted" 2. Set "Rerouted (Y/N)" to "Yes" 3. Select the Reroute Reason from the dropdown 4. Enter the new destination port/city in "Rerouted To" 5. Update the ETA accordingly
Project / Job Codes
Used primarily by DFF, AJK Unity, and Pearl Craft. Maintain codes in the "Project Codes" sheet.
Divisions
- Delmon Furniture Factory - Motor & Marine Division - Home Appliances Distribution - Home Appliances Service Center - Tire & Allied Business - AJK Unity - Pearl Craft